## Sheet1
System Name | COLLABORATIVE PROJECT MANAGEMENT TOOL
Members: | COCA, VAN HARVEY R.
SANTOS, MANWARUL FRANCIS C.
LUMAMBAS, JOHN ERIC E.
Statuses |  | Todo
In-Progress
Done
On-hold
|  |  |  | September |  |  | October | [30 empty] | November | [29 empty] | December
Tasks | Assignee | Date Started | Date Finished | Status | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1. User Authentication | Santos | 29/09/2024 | 2024-02-11 | Done
1.1 Log in | Santos | 29/09/2024 | 14/10/2024 | Done
1.2 Sign up | Santos | 15/10/2024 | 25/10/2024 | Done
1.3 Forgot Password | Santos | 26/10/2024 | 2024-02-11 | Done
1.4 Log out | Santos | 26/10/2024 | 2024-02-11 | Done
2. Task Management | Coca | 29/09/2024 | 2024-10-11 | In-Progress
2.1 Creating function adding Task | Coca | 29/09/2024 | 13/10/2024 | Done
2.2 Creating UI for the taskManagement | Coca | 29/09/2024 | 13/10/2024 | Done
2.3 Creating READ function | Coca | 29/09/2024 | 13/10/2024 | Done
2.4 Creating UPDATE function | Coca | 29/09/2024 | 2024-05-11 | On-hold
2.5 Make a filter and search function | Coca | 29/09/2024 | 2024-05-12 | On-hold
2.5 Creating Delete | Coca | 29/09/2024 | 13/10/2024 | Done
2.4 Clean up | Coca | 29/09/2024 | 13/10/2024 | Todo
2.5 Kanban boards | Coca | 27/10/2024 | 30/10/2024 | Todo
2.5 Calendar | Coca | 2024-01-11 | 2024-03-11 | Done
2.6 displaying deadlines calendar | Coca | 2024-01-11 | 2024-02-11 | In-Progress
2.7 fixing tooltip calendar | Coca | 2024-01-11 | 2024-02-11 | In-Progress
2.8 Fixing relationshipp between user models | Coca | 2024-02-11 | 2024-03-11 | On-hold
2.9 showing filtered tasks based on the project viewd | Coca | 2024-03-11 | 2024-10-11 | Todo
3.0 adding members based on the relationship | Coca | 2024-03-11 | 2024-10-11 | Todo
3. Real-Time Collaboration | Coca | 2024-10-11 | 2024-10-12 | Todo
3.1 add comments to tasks | Coca | 2024-10-11 | 2024-10-12 | Todo
3.2 add comments to the Project | Coca | 2024-10-11 | 2024-10-12 | Todo
3.3 adding notification | Coca | 2024-10-11 | 2024-10-12 | Todo
4. Document management and file sharing | Santos | 2024-05-11 | 19/11/2024 | Done
4.1 Get notifications about the project updates | Santos | 2024-05-11 | 19/11/2024 | Done
4.2 Creating the upload file | Santos | 14/11/2024 | 19/11/2024 | Done
4.3 Storing documents | Santos | 14/11/2024 | 19/11/2024 | Done
4.4 Search specific files | Santos | 14/11/2024 | 19/11/2024 | Done
5. Reporting and Analytics | Lumambas | 29/9/2024 |  | Done
5.1 Creating Home Page | Lumambas | 2024-08-10 | 20/10/2024 | Done
5.2 Creating views for projects data | Lumambas | 13/10/2024 | 14/10/2024 | Done
5.3 Creating Dashboard UI | Lumambas | 27/10/2024 | 30/10/2024 | Done
5.4 Implementing Dashboard html and css | Lumambas | 27/10/2024 | 30/10/2024 | Done
5.5 Creating Dashboard js and views | Lumambas | 27/10/2024 | 2024-04-12 | Done
5.6 Cleaning up | Lumambas | 2024-01-11 | 2024-03-12 | Done
6. Project page | Lumambas | 2024-04-10 | 2024-04-12 | Done
6.1 Creating Specific Project Page | Lumambas | 2024-04-10 | 16/10/2024 | Done
6.1.1 Creating the overview project page | Lumambas | 2024-04-10 | 16/10/2024 | Done
6.2 Creating Project List Page UI | Lumambas | 2024-10-10 | 2024-10-10 | Done
6.3 Creating Project List Page | Lumambas | 2024-11-10 | 17/10/2024 | Done
6.4 Creating function for adding Project | Lumambas | 13/10/2024 | 13/10/2024 | Done
6.5 Creating project list views | Lumambas | 13/10/2024 | 13/10/2024 | Done
6.6 Creating add project UI | Lumambas | 20/10/2024 | 24/10/2024 | Done
6.7 Implementing create project html and css | Lumambas | 20/10/2024 | 24/10/2024 | Done
6.8 Creating views for add project | Lumambas | 20/10/2024 | 24/10/2024 | Done
6.9 Creating modal ui for delete project | Lumambas | 20/10/2024 | 24/10/2024 | Done
6.10 Implementing modal html and css | Lumambas | 20/10/2024 | 24/10/2024 | Done
6.11 Creating delete project views | Lumambas | 20/10/2024 | 24/10/2024 | Done
6.12 Creating project details ui | Lumambas | 24/10/2024 | 26/10/2024 | Done
6.13 Implenting project details html and css | Lumambas | 24/10/2024 | 26/10/2024 | Done
6.14 Creating project detail views | Lumambas | 24/10/2024 | 26/10/2024 | Done
6.15 Creating add member UI | Lumambas | 28/10/2024 | 2024-07-11 | Done
6.16 Implementing Add member html and css | Lumambas | 28/10/2024 | 2024-07-11 | Done
6.17 Creating add member views and js | Lumambas | 28/10/2024 | 2024-07-11 | Done
6.18 Clean up | Lumambas | 18/11/2024 | 20/11/2024 | Done
6.19 Merging with other branches | Lumambas | 28/10/2024 | 30/10/2024 | Done
6.20 Create Modal UI for edit projects | Lumambas | 2024-09-11 | 2024-04-12 | Done
6.21 Implementing edit projects html and css | Lumambas | 2024-09-11 | 2024-04-12 | Done
6.22 Creating js and views for edit projects | Lumambas | 2024-09-11 | 2024-04-12 | Done